## Timeline
Sprint | Week
Setup/Planning | 0
Sprint 1 - Jan 17th - Jan 31st | 1 - 2
Sprint 2 - Jan 31st - Feb 14th | 3 - 4
Submission on Feb 17th | 5
Landmark | Date | Day | Past | Task Completed | Notes | Commit | Number | Author | Time | Description
Sprint 1 | 2020-01-17 | F | X | Draft outline of Model classes | Very rough - skeleton for bottom-up development | 1 | '14828cd | Duncan Wright | 80 minutes ago | Database pulling all data from completed games'
Weekend start Sprint 1 | 2020-01-18 | S | X | Game class created, user give number of opponents |  | 2 | '79314b5 | Graham Darroch | 2 hours ago | Game recording number of rounds won per player and number of draws total'
Weekend start Sprint 1 | 2020-01-19 | S | X |  |  | 3 | '12a7915 | Graham Darroch | 4 hours ago | Some new tests in GameTest'
| 2020-01-20 | M | X | Deck updated with unique spaceship names |  | 4 | '33e1c67 | Graham Darroch | 5 hours ago | Deck builder test added'
| 2020-01-21 | T | X | Database query started - awaiting final shape compareStats working getHand method to Player to see cards |  | 5 | '922e404 | Duncan Wright | 18 hours ago | Player attributes now highlight on mouse over'
| 2020-01-22 | W | X | Added roundCount etc reformat to src folder |  | 6 | '93e1a5c | Duncan Wright | 19 hours ago | Added some fun jquery examples'
| 2020-01-23 | T | X | Removes inactive players show winner message |  | 7 | '5afff7b | Duncan Wright | 20 hours ago | ModelDeckBuilder and Quit functionality'
| 2020-01-24 | F | X |  |  | 8 | 'bd85771 | Duncan Wright | 23 hours ago | Merge https://github.com/dawwestk/ITGroupProject'
Weekend mid-Sprint 1 | 2020-01-25 | S | X | Refactor, removed Round class |  | 9 | '0d98d08 | Duncan Wright | 23 hours ago | Database Query added to CLI application'
Weekend mid-Sprint 1 | 2020-01-26 | S | X |  |  | 10 | '9603d0a | Duncan Wright | 23 hours ago | Database Query added to CLI application'
| 2020-01-27 | M | X |  |  | 11 | '99f93ae | dawwestk | 25 hours ago | Add files via upload'
| 2020-01-28 | T | X | User can quit after any round (or at start of new game) |  | 12 | 'c97b524 | Duncan Wright | 2 days ago | Initial JavaScript and HTML mock-up'
| 2020-01-29 | W | X | Database Link finalised | Information is successfully read/written to localhost | 13 | '87eba64 | Duncan Wright | 2 days ago | Added assets folder to host media'
| 2020-01-30 | T | X |  |  | 14 | 'ac27a86 | Duncan Wright | 2 days ago | Updated POM file with DB driver dependency'
End of Sprint 1 | 2020-01-31 | F | X |  |  | 15 | 'cdef74a | Graham Darroch | 3 days ago | Bug fix in hasWinner() in Game'
Weekend between Sprints | 2020-02-01 | S |  |  |  | 16 | '3eb3fb4 | Graham Darroch | 4 days ago | Refactored command line input/output out of Game class'
Weekend between Sprints | 2020-02-02 | S |  |  |  | 17 | '306fe5d | Graham Darroch | 4 days ago | Refactor of hasWinner() method'
Sprint 2 | 2020-02-03 | M |  |  |  | 18 | '00908c7 | Graham Darroch | 4 days ago | Refactor of Round class'
| 2020-02-04 | T |  |  |  | 19 | '476209e | Graham Darroch | 4 days ago | Refactored Game class'
| 2020-02-05 | W |  |  |  | 20 | 'f5388ce | Graham Darroch | 4 days ago | Minor refactors'
| 2020-02-06 | T |  |  |  | 21 | '1e622d6 | Graham Darroch | 5 days ago | Qualified attribute and method references with this for clarity'
| 2020-02-07 | F |  |  |  | 22 | '76cc446 | Graham Darroch | 5 days ago | Fix potential resource leak. Removed redundant code.'
Weekend mid-Sprint 2 | 2020-02-08 | S |  |  |  | 23 | '8e7aba6 | Duncan Wright | 5 days ago | Off-by-1 error in statPicker resolved'
Weekend mid-Sprint 2 | 2020-02-09 | S |  |  |  | 24 | '57fd9d2 | Graham Darroch | 5 days ago | Isolated re-usable game classes into game package'
| 2020-02-10 | M |  |  |  | 25 | 'd942794 | Graham Darroch | 5 days ago | Fixing a broken eclipse configuration issue'
| 2020-02-11 | T |  |  |  | 26 | '114229e | Graham Darroch | 5 days ago | Removed .classpath from cached files'
| 2020-02-12 | W |  |  |  | 27 | 'b59c38c | Graham Darroch | 5 days ago | Removed incorrectly cached files'
| 2020-02-13 | T |  |  |  | 28 | '213ab49 | Duncan Wright | 5 days ago | Commented ModelCard for ease of use'
End of Sprint 2 | 2020-02-14 | F |  |  |  | 29 | '84b70ea | Duncan Wright | 5 days ago | Back to Dictionary/hashmap and bug fixes implemented'
Weekend (last minute touches) | 2020-02-15 | S |  |  |  | 30 | '6ffaa4e | Caimpson | 5 days ago | Turned automatic CLI mode off'
Weekend (last minute touches) | 2020-02-16 | S |  |  |  | 31 | '96ed9b6 | Caimpson | 5 days ago | Fixed getHighest bug'
Submission | 2020-02-17 | M |  |  |  | 32 | '3ba0932 | dawwestk | 6 days ago | Update Round.java'
[6 empty] | 33 | '3ff9757 | Duncan Wright | 6 days ago | Undoing ModelCard dictionary until tested'
[6 empty] | 34 | 'f5ea552 | Duncan Wright | 6 days ago | ModelCard now working with dictionary'
[6 empty] | 35 | '3989a70 | Duncan Wright | 6 days ago | ModelCard now working with dictionary'
[6 empty] | 36 | '90e9661 | Duncan Wright | 6 days ago | ModelCard now working with dictionary'
[6 empty] | 37 | '7166b9e | Duncan Wright | 6 days ago | ModelCard now working with dictionary'
[6 empty] | 38 | 'fa5ad73 | Duncan Wright | 6 days ago | Tidied up some outputs and method calls'
[6 empty] | 39 | '846d29a | dawwestk | 6 days ago | Updated getHighestAttribute'
[6 empty] | 40 | 'af2ad0a | Graham Darroch | 6 days ago | Merge branch 'master' of https://github.com/dawwestk/ITGroupProject'
[6 empty] | 41 | 'e612a5f | Graham Darroch | 6 days ago | Updated pom to include surefire test plugin'
[6 empty] | 42 | '610f660 | Graham Darroch | 6 days ago | Moved source files from /src to /src/main/java'
[6 empty] | 43 | 'f11317f | Mark Darroch | 6 days ago | Winner Message.'
[6 empty] | 44 | 'a138b66 | Mark Darroch | 6 days ago | Reworked activePlayers. Commented out the continueChoice cause it was becoming a pisstake.'
[6 empty] | 45 | '3ac7f74 | Duncan Wright | 6 days ago | Removes players with 0 cards on draw condition'
[6 empty] | 46 | '22820be | Graham Darroch | 6 days ago | Changed class name to match filename'
[6 empty] | 47 | '5ad5dc0 | Graham Darroch | 6 days ago | Scoped junit to test scope and made tests public'
[6 empty] | 48 | '49508ff | Duncan Wright | 6 days ago | Removing players with 0 cards'
[6 empty] | 49 | '8893b72 | Graham Darroch | 6 days ago | Tests now runnable with mvn test'
[6 empty] | 50 | '949e467 | dawwestk | 6 days ago | Update TopTrumpsCLIApplication.java'
[6 empty] | 51 | '7aab14d | dawwestk | 6 days ago | Update Game.java'
[6 empty] | 52 | 'a9cffe9 | Duncan Wright | 6 days ago | Winning activeCard is moved to back of hand'
[6 empty] | 53 | '5a0923d | Mark Darroch | 6 days ago | Added a continueGame switch in CLI.'
[6 empty] | 54 | 'af8342d | Mark Darroch | 6 days ago | Added a method to remove players with empty hands.'
[6 empty] | 55 | '6569d02 | Mark Darroch | 6 days ago | Added a continueGame switch in CLI.'
[6 empty] | 56 | 'abeb3bc | Duncan Wright | 6 days ago | CommunalPile fixed for draw condition'
[6 empty] | 57 | '7f27d81 | Duncan Wright | 6 days ago | Merge https://github.com/dawwestk/ITGroupProject'
[6 empty] | 58 | '026a52a | Duncan Wright | 6 days ago | CommunalPile fixed for draw condition'
[6 empty] | 59 | 'b9237a5 | Mark Darroch | 6 days ago | Added a continueGame switch in CLI.'
[6 empty] | 60 | '960bb40 | Mark Darroch | 6 days ago | Added a deckSize method. It returns createdCards in the deck method. Unsure if that is the correct one to return.'
[6 empty] | 61 | '7901b2f | Caimpson | 6 days ago | Fixed bugs in Round and Game.performRound so correct winner of round is set
[6 empty] | 62 | '01d6f7f | Graham Darroch | 7 days ago | Unit test skeleton files'
[6 empty] | 63 | 'd6df593 | Graham Darroch | 7 days ago | GameTests won't compile until a method is added to Game.java (deckSize())'
[6 empty] | 64 | '1b1c86d | Mark Darroch | 7 days ago | Removed another test printout'
[6 empty] | 65 | '7c5e2ae | Mark Darroch | 7 days ago | Moved the roundCount increment to the correct place.'
[6 empty] | 66 | '6a65c97 | Mark Darroch | 7 days ago | Deleted the roundCount test printout.'
[6 empty] | 67 | '4a6b736 | Mark Darroch | 7 days ago | fixed a player name issue.'
[6 empty] | 68 | 'a0bde60 | Mark Darroch | 7 days ago | Merge branch 'master' of https://github.com/dawwestk/ITGroupProject'
[6 empty] | 69 | '9534b93 | Mark Darroch | 7 days ago | Fixed the roundCount bug. Added some printouts for context.'
[6 empty] | 70 | '6502e8f | dawwestk | 7 days ago | Update TopTrumps.java'
[6 empty] | 71 | '464fef0 | dawwestk | 7 days ago | Update DatabaseQuery.java'
[6 empty] | 72 | '42012ce | Duncan Wright | 7 days ago | Minor fix in game'
[6 empty] | 73 | 'e654887 | dawwestk | 7 days ago | Merge pull request #2 from dawwestk/dunc-branch'
[6 empty] | 74 | '81afa40 | dawwestk | 7 days ago | Merge branch 'master' into dunc-branch'
[6 empty] | 75 | 'b5f2564 | Duncan Wright | 7 days ago | changed Round to use booleans
[6 empty] | 76 | 'e16a92d | Caimpson | 7 days ago | merge'
[6 empty] | 77 | '6625130 | Caimpson | 7 days ago | Slight changes to Game and Round'
[6 empty] | 78 | '36db2b9 | Graham Darroch | 7 days ago | Added to package commandline'
[6 empty] | 79 | '0402fe1 | Mark Darroch | 7 days ago | Added a pre-game choice selection into the game loop in TopTrumpsCLIApplication. Commented out the DatabaseQuery.java temporarily.'
[6 empty] | 80 | 'df41c2f | Duncan Wright | 7 days ago | Re-adding DatabaseQuery class'
[6 empty] | 81 | 'a566f88 | Duncan Wright | 7 days ago | Removed DRAFT outline folder - all in src now'
[6 empty] | 82 | 'e63fca5 | Caimpson | 7 days ago | Merge'
[6 empty] | 83 | '17974d0 | Caimpson | 7 days ago | Bug Fix in Round where if 1st player won result is always draw'
[6 empty] | 84 | '6d05e96 | Duncan Wright | 7 days ago | Player method addToHand now adds to index 0'
[6 empty] | 85 | '2418a31 | Caimpson | 8 days ago | Continued work on Game.performRound
[6 empty] | 86 | '1ce4f08 | Caimpson | 8 days ago | Edited Round class so that only compareStat() methodis needed. This now returns either a single Player object representing the winner of the round
[6 empty] | 87 | 'e859f4f | Graham Darroch | 8 days ago | Bug fix. commandLineMode changed to false.'
[6 empty] | 88 | 'b63efca | Graham Darroch | 8 days ago | Merge branch 'master' of https://github.com/dawwestk/ITGroupProject'
[6 empty] | 89 | 'ffc5ca5 | Graham Darroch | 8 days ago | modified .gitignore to include entire target directory'
[6 empty] | 90 | '7076443 | Mark Darroch | 8 days ago | Set acceptable parameters for the category choice. Program will now only accept 1-5.'
[6 empty] | 91 | '13d8e5d | Graham Darroch | 8 days ago | removed cached .class files'
[6 empty] | 92 | '4249208 | Graham Darroch | 8 days ago | another modification of .gitignore'
[6 empty] | 93 | 'ca8060b | Graham Darroch | 8 days ago | gitignore changed again'
[6 empty] | 94 | '9f77056 | Graham Darroch | 8 days ago | gitignore change'
[6 empty] | 95 | '057d927 | Graham Darroch | 8 days ago | new gitignore for .class files after refactor'
[6 empty] | 96 | 'e314b45 | Graham Darroch | 8 days ago | Merge branch 'master' of https://github.com/dawwestk/ITGroupProject'
[6 empty] | 97 | 'b335089 | Graham Darroch | 8 days ago | modified .gitignore again'
[6 empty] | 98 | '63bdd36 | Duncan Wright | 8 days ago | Rounds and Games now run
[6 empty] | 99 | 'bbf8ca4 | Duncan Wright | 8 days ago | Minor compilation fix'
[6 empty] | 100 | '4f6781c | Mark Darroch | 8 days ago | Merge branch 'mark-branch''
[6 empty] | 101 | '5f252f6 | Mark Darroch | 8 days ago | test'
[6 empty] | 102 | '1540a6b | Mark Darroch | 8 days ago | test'
[6 empty] | 103 | '34ea5c8 | Mark Darroch | 8 days ago | Merge branch 'master' of https://github.com/dawwestk/ITGroupProject'
[6 empty] | 104 | 'd278ee0 | Mark Darroch | 8 days ago | test'
[6 empty] | 105 | '45fe1d3 | Caimpson | 8 days ago | Round class update'
[6 empty] | 106 | 'fe27d5f | Caimpson | 8 days ago | Deleted Round for re-commiting'
[6 empty] | 107 | 'b97cac7 | Caimpson | 8 days ago | Added Round Class'
[6 empty] | 108 | '473de7a | Mark Darroch | 8 days ago | test'
[6 empty] | 109 | 'cd9a391 | Mark Darroch | 8 days ago | Added a getHand method to Player'
[6 empty] | 110 | '728e205 | Mark Darroch | 8 days ago | reworked activePlayers. Added updated deck.txt.'
[6 empty] | 111 | '043460f | Graham Darroch | 8 days ago | modified .gitignore'
[6 empty] | 112 | '81d1062 | Graham Darroch | 8 days ago | modified .gitignore'
[6 empty] | 113 | '9a4d413 | Mark Darroch | 8 days ago | Merge branch 'master' of https://github.com/dawwestk/ITGroupProject into marks-branch'
[6 empty] | 114 | '9776d44 | Graham Darroch | 8 days ago | modified .gitignore'
[6 empty] | 115 | '07a3915 | Graham Darroch | 8 days ago | Added junit dependency'
[6 empty] | 116 | '0a630fc | Graham Darroch | 8 days ago | Fixed master'
[6 empty] | 117 | '6f28b76 | gdarroch | 8 days ago | Merge pull request #1 from dawwestk/master_backup'
[6 empty] | 118 | '4047b81 | Mark Darroch | 9 days ago | Added a getHand method to Player'
[6 empty] | 119 | '29462a2 | Mark Darroch | 9 days ago | Fixed the activePlayers method.'
[6 empty] | 120 | 'd3d52c2 | Mark Darroch | 9 days ago | Fixed the activePlayers method.'
[6 empty] | 121 | '8cd382a | Mark Darroch | 9 days ago | Reworked the Game class to remove the main statement. Combined BuildDeck
[6 empty] | 122 | 'c70b968 | Graham Darroch | 9 days ago | updated gitignore'
[6 empty] | 123 | '0943470 | Graham Darroch | 9 days ago | added command line tests'
[6 empty] | 124 | '1f9aef9 | Graham Darroch | 9 days ago | created initial command line test class'
[6 empty] | 125 | 'b35aad7 | Mark Darroch | 9 days ago | Project with draft files placed into the commandline package to make cloning easier.'
[6 empty] | 126 | 'c7dd893 | Duncan Wright | 9 days ago | Re-uploading Excel template as CSV'
[6 empty] | 127 | '4c0ca90 | Duncan Wright | 9 days ago | DatabaseQuery class created.'
[6 empty] | 128 | '3422f7a | Duncan Wright | 9 days ago | Added Excel template for database'
[6 empty] | 129 | '354eb52 | Duncan Wright | 9 days ago | StarCitizenDeck.txt names updated to remove duplicates'
[6 empty] | 130 | '01767a9 | mgdarroch | 11 days ago | Update Game.java'
[6 empty] | 131 | 'd9a65b6 | Duncan Wright | 12 days ago | Asks user for opponents
[6 empty] | 132 | '19459b8 | Duncan Wright | 12 days ago | Updated Card
[6 empty] | 133 | 'b9d439b | dawwestk | 12 days ago | Adding DRAFT outline of the model classes'
[6 empty] | 134 | '6ffa3a2 | Caimpson | 2 weeks ago | added template docs'
[6 empty] | 135 | '550c516 | dawwestk | 2 weeks ago | Initial commit'
Formulas:
Past = IF(TODAY() >= [Date],"X", "")

## User Stories Sprint 1
Story | Story ID | Priority | MoSCoW | Effort | Actual Effort | Test | Comment (just for us)
As a human player, I want to be able to choose whether to play top trumps online or on the command line. Priority: 10 Effort: 2 | 1 | 10 | Should | 2 | 1 |  | Already done by template program
As a human player, I want to be able to select the number of AI opponents. Priority: 10 Effort: 3 | 2 | 10 | Should | 3 | 2 |  | Simple scanner used with switch statement
As a human player I want to have the option of starting a new game after finishing one. Priority: 8 Cost: 1 | 3 | 8 | Should | 1 | 3 |  | Wasn't given to us - needed Game class to be well formed
I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | 4 | 6 | Could | 5 | 7 |  | Pulls from database, shows only aggregated stats
As a human player, I want to be able to select an attribute on my active top trumps card. Priority: 10 Effort: 3 | 5 | 10 | Must | 3 | 3 |  | Took about as much effort as expected
I want to be able to quit. Priority: 8 Cost: 1 | 6 | 8 | Should | 1 | 2 |  | Can quit at end of every round, or start of every game
As a user I want to see my top card Priority: 7 Cost 1 | 7 | 7 | Must | 1 | 2 |  | Card/Player impementation took some planning
As a user I want to be able to view aggregate statistics of past games Priority: 8 Cost 4 | 8 | 8 | Could | 4 | 5 |  | Stats are available - DB connection is stable (assumed set up is complete beforehand)
Who has won should be displayed each round Priority: 9 Cost: 1 | 9 | 9 | Should | 1 | 1 |  | Simple to implement after round winner has been decided

## Tasks Sprint 1
Story ID | Story | Task | Test | Points | Original Cost | Actual Cost | Notes
1 | As a human player, I want to be able to choose whether to play top trumps online or on the command line. Priority: 10 Effort: 2 | Provided in template | Manual Test |  | 2 | 1
2 | As a human player, I want to be able to select the number of AI opponents. Priority: 10 Effort: 3 | Created Scanner to get user input | Manual Test |  | 3 | 2
2 | As a human player, I want to be able to select the number of AI opponents. Priority: 10 Effort: 3 | Test validity of input | Unit Test
5 | As a human player, I want to be able to select an attribute on my active top trumps card. Priority: 10 Effort: 3 | Create view of card data |  |  | 3 | 3
5 | As a human player, I want to be able to select an attribute on my active top trumps card. Priority: 10 Effort: 3 | Use scanner to get user input
5 | As a human player, I want to be able to select an attribute on my active top trumps card. Priority: 10 Effort: 3 | Validate user entry
5 | As a human player, I want to be able to select an attribute on my active top trumps card. Priority: 10 Effort: 3 | Pass to switch statement
7 | As a user I want to see my top card Priority: 7 Cost 1 | Player, Card classes created to store data |  |  | 1 | 2
7 | As a user I want to see my top card Priority: 7 Cost 1 | Create view of card data
9 | Who has won should be displayed each round Priority: 9 Cost: 1 |  |  |  | 1 | 1
3 | As a human player I want to have the option of starting a new game after finishing one. Priority: 8 Cost: 1 | Created Game class to provide new object | Potential Unit Test |  | 1 | 3
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | Create databaseQuery object |  |  | 5 | 6
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | Take in User String for connection
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | Create table in DB server environment
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | Pull data from table
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | Validate data
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | Display data to user
6 | I want to be able to quit. Priority: 8 Cost: 1 | Use scanner to get user input at the end of a round |  |  | 1 | 2
6 | I want to be able to quit. Priority: 8 Cost: 1 | Create some sort of break to allow user to quit at any time
8 | As a user I want to be able to view aggregate statistics of past games Priority: 8 Cost 1 | Read from database object |  |  | 4 | 5
[5 empty] | 21 | 25

## User Stories Sprint 2
Story | Story ID | Priority | MoSCoW | Effort | Actual Effort | Test | Comment (just for us)

## Tasks Sprint 2
Story ID | Story | Task | Test | Points | Original Cost | Actual Cost | Notes
[5 empty] | 0 | 0

## Template Burndown
Story ID | Sprint 1 Backlog | Completed | Original Cost | Actual Cost
1 | Provided in template | X | 2 | 1
2 | Created Scanner to get user input | X | 3 | 2
2 | Test validity of input
3 | Created Game class to provide new object | X | 3 | 3
4 | Create databaseQuery object
4 | Take in User String for connection
4 | Create table in DB server environment | X | 1 | 2
4 | Pull data from table
4 | Validate data | X | 1 | 1
4 | Display data to user | X | 1 | 3
5 | Create view of card data | X | 5 | 6
5 | Use scanner to get user input
5 | Validate user entry
5 | Pass to switch statement
6 | Use scanner to get user input at the end of a round | X | 1 | 0
6 | Create some sort of break to allow user to quit at any time
7 | Player, Card classes created to store data
7 | Create view of card data
8 | Read from database object | X | 1 | 0
9 | Who has won should be displayed each round
Total
[6 empty] | Two Week Sprint Mon - Friday |  |  | Two Week Sprint Mon - Friday
[6 empty] | Sprint 1 - Days | Plan | Actual | Sprint 1 - Days | Plan | Actual
Story ID | Story | Priority | MoSCoW | Effort | Actual Effort | 1 | 18 | 19 | 1 | 18 | 19
1 | As a human player, I want to be able to choose whether to play top trumps online or on the command line. Priority: 10 Effort: 2 | 10 | Should | 2 | 1 | Already done by template program | 16 | 18 | 2 | 16 | 18
2 | As a human player, I want to be able to select the number of AI opponents. Priority: 10 Effort: 3 | 10 | Should | 3 | 2 | Simple scanner used with switch statement | 13 | 16 | 3 | 13 | 16
3 | As a human player I want to have the option of starting a new game after finishing one. Priority: 8 Cost: 1 | 8 | Should | 1 | 3 | Wasn't given to us - needed Game class to be well formed | 12 | 13 | 4 | 12 | 13
4 | I want to be able to view statistics concerning past games and scores. Priority: 6 Cost: 8 | 6 | Could | 5 | 7 | Pulls from database, shows only aggregated stats | 7 | 8 | 5 | 7 | 8
5 | As a human player, I want to be able to select an attribute on my active top trumps card. Priority: 10 Effort: 3 | 10 | Must | 3 | 3 | Took about as much effort as expected | 4 | 5 | 6 | 4 | 5
6 | I want to be able to quit. Priority: 8 Cost: 1 | 8 | Should | 1 | 2 | Can quit at end of every round, or start of every game | 3 | 4 | 7 | 3 | 4
7 | As a user I want to see my top card Priority: 7 Cost 1 | 7 | Must | 1 | 2 | Card/Player impementation took some planning | 2 | 2 | 8 | 2 | 2
8 | As a user I want to be able to view aggregate statistics of past games Priority: 8 Cost 4 | 8 | Could | 4 | 5 | Stats are available - DB connection is stable (assumed set up is complete beforehand) | 1 | 1 | 9 | 1 | 1
9 | Who has won should be displayed each round Priority: 9 Cost: 1 | 9 | Should | 1 | 1 | Simple to implement after round winner has been decided | 0 | 0 | 10 | 0 | 0
|  |  |  | 21 | 26

## Template
User Story ID | As a <type of user> | I want to… <perform some task> | … so that I can <achieve some goal> | Priority | Effort/Cost | Story Complete (Y/N) | Code Complete (Feature active) | Completion Date
Links I used | https://www.smartsheet.com/writing-user-story
https://www.smartsheet.com/user-story-templates